## Projects
| Status | Category | Audience | SME | Lead | Support | E-Learning | Job Aid | QRG | Coaching Guide (GROW) | Team Time Guide | Video | PPT | Facilitator Guide | Participant Guide | DIY Activity | Knowledge Check | Assessment | Communication | Learner Activity | Scenarios -Role Plays | Other - see notes | Level | Start Date | Due Date | Planned Days | D'Andre Review | TD First Review | SME Review | TD Final Review | Available Date | Actual Days | Days Prior to Pause
2024 Compliance Courses | C | Compliance | All Bank |  | Roy | Jenn | [16 empty] | M | 2023-07-10 | 2023-12-01 | 105 |  |  |  |  | 2023-12-01 | 105
2025 Compliance Curriculum | C | Compliance | All Bank | Roy, D'Andre | Roy | [16 empty] | x | L | 2024-09-23 | 2024-11-04 | 31 |  |  |  |  | 2024-10-18 | 20
Additional Learning & Growth 2024 | C | Team Member Development | All Bank | Roy | Roy |  | x | [15 empty] | L | 2023-12-18 | 2023-12-20 | 3 |  |  |  |  | 2023-12-18 | 1
Additional Training Power BI | C | Projects | All Bank | Roy | Roy | D'Andre | [15 empty] | x | M | 2023-09-18 | 2023-09-30 | 10 |  |  |  |  | 2023-09-26 | 7
Advanced Member Experiences | C | Technical Skills | Retail Branches | Nora | Roy | Sarah | [6 empty] | x | x | x | [7 empty] | M | 2023-07-14 | 2023-09-13 | 44 |  |  |  |  | 2023-09-13 | 44
Advanced TEAM Time Guides | C | Technical Skills | Retail Branches | Nora | Roy | Jenn |  |  |  |  | x | [11 empty] | L | 2023-07-14 | 2023-09-20 | 49 |  |  |  |  | 2023-09-13 | 44
August Leveling Up | C | Team Member Development | All Bank | Roy | Roy | [13 empty] | x |  |  |  | L | 2023-07-26 | 2023-08-01 | 5 |  |  |  |  | 2023-07-31 | 4
Branch Consult Midtown Dec. | C | Team Member Development | Retail Branches | Roy | Roy | [13 empty] | x |  |  |  | L | 2024-12-18 | 2024-12-18 | 1 |  |  |  |  | 2024-12-18 | 1
Branch Consult N. Oak Jan. | C | Team Member Development | Retail Branches | Roy | Roy | [13 empty] | x |  |  |  | L | 2025-01-17 | 2025-01-17 | 1 |  |  |  |  | 2025-01-17 | 1
Branch Consult Troost Dec. | C | Team Member Development | Retail Branches | Roy | Roy | [13 empty] | x |  |  |  | L | 2024-12-20 | 2024-12-20 | 1 |  |  |  |  | 2024-12-20 | 1
Branch Consult Troost Dec. 2 | C | Team Member Development | Retail Branches | Roy | Roy | [13 empty] | x |  |  |  | L | 2024-12-18 | 2024-12-18 | 1 |  |  |  |  | 2024-12-18 | 1 | 30
Business Accounts Course | C | Technical Skills | Retail Branches | McKensy | Roy | [7 empty] | x | x | x |  |  |  |  | x | x |  | L | 2024-01-02 | 2024-03-14 | 53 |  |  |  |  | 2024-03-07 | 48
Business Accounts Outline | C | Technical Skills | Retail Branches | Roy | Roy | [16 empty] | x | M | 2023-05-01 | 2023-05-19 | 15 |  |  |  |  | 2023-05-17 | 13
Capture Additional Training in LMS | C | Team Member Development | All Bank | D'Andre, Mel | Roy | D'Andre | x | x | [8 empty] | x |  | x |  |  | x | M | 2023-06-08 | 2023-07-21 | 32 | 2023-07-18 |  |  | 2023-07-19 | 2023-07-19 | 30
Cashier's Check | C | Technical Skills | Retail Branches | McKensy | Roy | [5 empty] | x | [11 empty] | L | 2024-06-12 | 2024-08-01 | 37 |  |  |  |  | 2024-07-31 | 36
Competencies Library Dynamic Learning | C | Projects | All Bank | Roy | Roy | D'Andre | [15 empty] | x | M | 2024-12-16 | 2025-01-28 | 32 |  |  |  |  | 2025-01-14 | 22
CRM For Small BB part 2 | A | Projects | Team Members | Roy | Roy | [13 empty] | x |  |  | x | L | 2025-02-11 | 2025-03-05 | 17 | [5 empty] | -32642
December Leveling Up | C | Team Member Development | All Bank | Roy | Roy | [13 empty] | x |  |  |  | L | 2023-11-24 | 2023-12-01 | 6 |  |  |  |  | 2023-11-29 | 4
Developing Your People | A | Leadership Development | Leaders | D'Andre | D'Andre | [6 empty] | x | x |  | x | [7 empty] | M | 2025-02-19 | 2025-03-07 | 13 | [5 empty] | -32648
Developing Your People - Connect Classroom | A | Leadership Development | Leaders | D'Andre | D'Andre | [16 empty] | X | M | 2025-03-07 | 2025-03-21 | 11 | [5 empty] | -32660
Digital Banking Update | C | Technical Skills | All Bank | Roy | Roy |  | x | [15 empty] | L | 2023-11-27 | 2023-12-01 | 5 |  |  |  |  | 2023-11-30 | 4
Dynamic CRM for SmallBusiness | C | Projects | Other | SeanLynch, D'Andre Sean | Roy |  |  | x | [14 empty] | H | 2024-04-23 | 2024-12-10 | 166 |  |  |  |  | 2024-12-03 | 161
Enrolling in Courses in LMS | C | Technical Skills | All Bank | D'Andre | Roy |  |  |  | x | [12 empty] | x | L | 2023-09-26 | 2023-12-01 | 49 |  |  |  |  | 2023-12-01 | 49
Feb Development Comm - Leader Revision | C | Leadership Development | Leaders | D'Andre | D'Andre | [13 empty] | x |  |  |  | L | 2025-02-18 | 2025-02-19 | 2 |  |  |  |  | 2025-02-19 | 2
Feb Development Comm - Reminder | C | Team Member Development | All Bank | D'Andre | D'Andre | [13 empty] | x |  |  |  | L | 2025-02-18 | 2025-02-19 | 2 |  |  |  |  | 2025-02-19 | 2
Feb Development Communication | C | Team Member Development | All Bank | D'Andre | D'Andre | [13 empty] | x |  |  |  | L | 2025-02-03 | 2025-02-07 | 5 |  |  |  |  | 2025-02-04 | 2
Fundamental Member Experiences | C | Technical Skills | Retail Branches | Nora | Roy | Sarah | [6 empty] | x | x | x | x |  |  |  | x | x |  | H | 2023-06-05 | 2023-09-01 | 65 |  |  |  |  | 2023-09-01 | 65
Golden Circle- -SLT | A | Leadership Development | Leaders | Sean, Tim, D'Andre | D'Andre | [6 empty] | x | x | [9 empty] | M | 2025-01-28 | 2025-02-25 | 21 | [5 empty] | -32632
Image Center Update to Materials Part 1 | C | Technical Skills | Retail Branches | Alex | Roy | Sarah | x | x | x |  | x |  | x | x | x | x |  |  |  | x | x |  | L | 2024-09-24 | 2024-10-11 | 14 |  |  |  |  | 2024-11-29 | 49
Image Center Update to Materials Part 2 | C | Technical Skills | Retail Branches | Alex | Roy | Sarah | x | x | x |  | x |  | x | x | x | x |  |  |  | x | x |  | L | 2024-09-24 | 2024-10-11 | 14 |  |  |  |  | 2024-11-29 | 49
July Leveling Up | C | Team Member Development | All Bank | Roy | Roy | [13 empty] | x |  |  |  | L | 2023-06-19 | 2023-06-23 | 5 |  | 2023-06-21 |  |  | 2023-06-21 | 3
June Leveling Up | C | Team Member Development | All Bank | Roy | Roy | [13 empty] | x |  |  |  | L | 2023-05-16 | 2023-05-26 | 9 | 2023-05-22 | 2023-05-22 |  |  | 2023-05-22 | 5
Lead Measure Tracking | U | Projects | Other | D'Andre | Roy | [16 empty] | x | H | 2024-02-15 | 2024-04-26 | 52 | [5 empty] | -32384
Learning Plan Cirriculum Update | A | Member Experience | Retail Branches | Roy | Roy | Jenn |  |  |  |  | x | [7 empty] | x |  |  |  | M | 2025-02-26 | 2025-02-28 | 3 | [5 empty] | -32653
LMS Compliance Assignment Spreadsheet | C | Projects | All Bank | Roy | Roy | [16 empty] | x | M | 2023-09-26 | 2023-10-12 | 13 |  |  |  |  | 2023-10-12 | 13
LMS Compliance Dashboard | C | Projects | All Bank | D'Andre | Roy | [16 empty] | x | M | 2023-09-08 | 2023-09-29 | 16 |  |  |  |  | 2023-09-14 | 5
LMS Dashboard | C | Technical Skills | All Bank | D'Andre | Roy |  |  |  | x | [12 empty] | x | L | 2023-09-26 | 2023-12-01 | 49 |  |  |  |  | 2023-12-01 | 49
Money Orders | C | Technical Skills | Retail Branches | McKensy | Roy | [5 empty] | x | [11 empty] | L | 2024-06-12 | 2024-08-01 | 37 |  |  |  |  | 2024-07-31 | 36
MRC Curriculum LMS | C | Technical Skills | Call Center | D'Andre | Roy | Jenn | [15 empty] | x | H | 2023-11-06 | 2023-12-31 | 40 |  |  |  |  | 2023-12-27 | 38
NMLS Renweal | C | Projects | All Bank | HR | Roy | [16 empty] | x | L | 2024-12-16 | 2024-12-31 | 12 |  |  |  |  | 2024-12-31 | 12
November Leveling Up | C | Team Member Development | All Bank | Roy | Roy | [13 empty] | x |  |  |  | L | 2023-10-20 | 2023-11-01 | 9 |  |  |  |  | 2023-11-01 | 9
October Leveling Up | C | Team Member Development | All Bank | Roy | Roy | [13 empty] | x |  |  |  | L | 2023-09-21 | 2023-10-01 | 7 |  |  |  |  | 2023-10-03 | 9
On -Us Checks | C | Technical Skills | Retail Branches | McKensy | Roy | [5 empty] | x | [11 empty] | L | 2024-06-12 | 2024-08-01 | 37 |  |  |  |  | 2024-07-31 | 36
Presentation for Overview of Personal Development Resources for Leaders | A | Leadership Development | Leaders | Roy | Roy | D'Andre | [6 empty] | x | [9 empty] | M | 2025-01-13 | 2025-01-28 | 12 | [5 empty] | -32621
Product and Service Survey | C | Member Experience | All Bank | D'Andre | Roy | [16 empty] | x | H | 2024-06-01 | 2024-06-28 | 20 |  |  |  |  | 2024-06-26 | 18
Product and Service Survey | C | Projects | Retail Branches | Roy | Roy | [16 empty] | x | L | 2024-03-27 | 2024-04-05 | 8 |  |  |  |  | 2024-04-16 | 15
RB Certification | C | Technical Skills | Retail Branches | McKensy | Roy | Sarah | x | [10 empty] | x |  |  |  |  | M | 2024-02-02 | 2024-03-15 | 31 |  |  |  |  | 2024-03-12 | 28
Reports in LMS | C | Technical Skills | All Bank | D'Andre | Roy |  |  |  | x | [12 empty] | x | L | 2023-09-26 | 2023-12-01 | 49 |  |  |  |  | 2023-12-01 | 49
Retail New RA Curriculum LMS | C | Technical Skills | Retail Branches | D'Andre | Roy | [16 empty] | x | H | 2024-05-22 | 2024-06-28 | 28 |  |  |  |  | 2024-06-28
Retail RA Curriculum LMS | C | Technical Skills | Retail Branches | D'Andre | Roy | Alex | [16 empty] | L | 2024-01-02 | 2024-02-29 | 43 |  |  |  |  | 1900-01-08 | -32347
Retail RB & Curriculum LMS | C | Technical Skills | Retail Branches | D'Andre | Roy | Alex | [15 empty] | x | H | 2023-12-12 | 2023-12-31 | 14 |  |  |  |  | 2023-12-29 | 14
September Leveling Up | C | Team Member Development | All Bank | Roy | Roy | [13 empty] | x |  |  |  | L | 2023-08-26 | 2023-09-08 | 10 |  |  |  |  | 2023-09-05 | 7
Supervisor Reporting Update | C | Leadership Development | Leaders | D'Andre | Roy | [16 empty] | x | L | 2024-12-16 | 2025-01-06 | 16 |  |  |  |  | 2025-01-06 | 16
Talent Development BankWiki Page Update | C | Projects | All Bank | D'Andre | Roy | [16 empty] | x | M | 2023-12-18 | 2024-01-18 | 24 | 1900-01-05 |  |  |  | 2024-01-18 | 24
TD Scorecard | C | Projects | All Bank | D'Andre | Roy | [16 empty] | x | H | 2023-05-01 | 2023-06-02 | 25 | 2023-05-30 |  |  |  | 2023-06-01 | 24
Team Huddle 1 | C | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-01-31 | 50 |  |  |  | 2024-11-27 | 2024-11-27 | 3
Team Huddle 10 | A | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-02-28 | 70 | [5 empty] | -32586
Team Huddle 11 | A | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-02-28 | 70 | [5 empty] | -32586
Team Huddle 12 | A | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-03-07 | 75 | [5 empty] | -32586
Team Huddle 2 | C | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-01-31 | 50 |  |  |  | 2024-11-27 | 2024-11-27 | 3
Team Huddle 3 | C | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-01-31 | 50 |  |  |  | 2024-11-27 | 2024-11-27 | 3
Team Huddle 4 | C | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-01-31 | 50 |  |  |  | 2024-11-27 | 2024-11-27 | 3
Team Huddle 5 | A | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-02-18 | 62 | [5 empty] | -32586
Team Huddle 6 | A | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-02-18 | 62 | [5 empty] | -32586
Team Huddle 7 | A | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-02-18 | 62 | [5 empty] | -32586
Team Huddle 8 | A | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-02-21 | 65 | [5 empty] | -32586
Team Huddle 9 | A | Member Experience | Retail Branches | Roy,D'Andre | Roy | Jenn | [13 empty] | x |  |  | L | 2024-11-25 | 2025-02-21 | 65 | [5 empty] | -32586
Team Member Personal Development Video | C | Team Member Development | All Bank | Roy | Roy | D'Andre | [5 empty] | x | [10 empty] | M | 2025-01-13 | 2025-02-07 | 20 |  |  |  |  | 2025-02-10 | 21
TEAM TIME Guide Update 1 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 10 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 11 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 12 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 13 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 14 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 15 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 16 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 17 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 18 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 19 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 2 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 20 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 21 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 22 | C | Technical Skills | Team Members | Roy, Jenn | Sarah | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 23 | C | Technical Skills | Team Members | Roy, Jenn | Roy | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 24 | C | Technical Skills | Team Members | Roy, Jenn | Roy | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 25 | C | Technical Skills | Team Members | Roy, Jenn | Roy | Jenn |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 26 | C | Technical Skills | Team Members | Roy, Jenn | Jenn | Sarah |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 27 | C | Technical Skills | Team Members | Roy, Jenn | Jenn | Sarah |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 3 | C | Technical Skills | Team Members | Roy, Jenn | Jenn | Sarah |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 4 | C | Technical Skills | Team Members | Roy, Jenn | Jenn | Sarah |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 5 | C | Technical Skills | Team Members | Roy, Jenn | Jenn | Sarah |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 6 | C | Technical Skills | Team Members | Roy, Jenn | Jenn | Sarah |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 7 | C | Technical Skills | Team Members | Roy, Jenn | Jenn | Sarah |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 8 | C | Technical Skills | Team Members | Roy, Jenn | Jenn | Sarah |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
TEAM TIME Guide Update 9 | C | Technical Skills | Team Members | Roy, Jenn | Jenn | Sarah |  |  |  |  | x | [11 empty] | L | 2024-11-01 | 2024-12-06 | 26 |  |  |  |  | 2024-12-01 | 21
Update Development Plan Resources | C | Projects | All Bank | Roy | Roy | D'Andre | [15 empty] | x | L | 2024-12-16 | 2025-02-07 | 40 |  |  |  |  | 2025-02-10 | 41
WAM Job Aid | C | Team Member Development | All Bank | D'Andre | Roy | D'Andre |  | x | [14 empty] | L | 2023-12-18 | 2024-01-18 | 24 |  |  |  |  | 2023-12-20 | 3
Formulas:
Planned Days = NETWORKDAYS([Start Date],[Due Date])
Actual Days = NETWORKDAYS([Start Date],[Available Date])